## Monitoring Piping
LOI Date | KOM Date | Schedule | Welding Map Date | Receive Dwg | Start Fabric | NS | AREA | System | Priority | Sub Area | Drawing No. | LINE NO | LINE CODE | MAT'L LINE | MAT'L CODE | PAGE | REV | FW / SW | JOINT TYPE | JOINT NO | PIPE SPOOL | DN | DIA-INCH PLAN SW | DIA-INCH PLAN FW | TOTAL | Comment | P LEGEND | P MATL CODE | P TYPE | P MATL TYPE | P GROUP MATL | P CLASS / SCH | P BASE SIZE 1 | P BASE SIZE 2 | P THK 1 | P Standard Matl Name | P QTY MATL | P UOM | S MATL CODE | S TYPE | S MATL TYPE | S GROUP MATL | S CLASS / SCH | S BASE SIZE 1 | S BASE SIZE 2 | S THK 1 | S Standard Matl Name | S QTY MATL | S UOM | T MATL CODE | T TYPE | T MATL TYPE | T GROUP MATL | T CLASS / SCH | T BASE SIZE 1 | T BASE SIZE 2 | T THK 1 | T Standard Matl Name | T QTY MATL | T UOM | MATL REMARKS | P SR / MIR NO | P SR DATE | P PIC | P QTY TOTAL | P QTY HAULING | P QTY OUTSTANDING | P QTY MAPPING | P MAPPING BALANCE | S SR / MIR NO | S SR DATE | S PIC | S QTY TOTAL | S QTY HAULING | S QTY OUTSTANDING | S QTY MAPPING | S MAPPING BALANCE | T SR / MIR NO | T SR DATE | T PIC | T QTY TOTAL | T QTY HAULING | T QTY OUTSTANDING | T QTY MAPPING | T MAPPING BALANCE | MIR REMARKS | FIT-UP RECORD SW | FIT-UP RECORD FW | FIT-UP RECORD DATE | FU SPV | WELDING RECORD SW | WELDING RECORD FW | WELDING RECORD DATE | W SPV | W STAMP | QAQC AFI F/U DATE | QAQC AFI F/U NO | QAQC AFI F/U RES | QAQC VISUAL DATE | QAQC VISUAL NO | QAQC VISUAL RES | PPC CLAIM REPORT FABS 30% | PPC CLAIM REPORT INSTALL 60% | PPC CLAIM REPORT PUNCHLIST 10% | PPC CLAIM REPORT TOTAL | SUMMARY AFI | LAST PERIOD | THIS PERIOD | CUMM | Remarks | PK
2025-03-01 | 2025-03-07 | 2025-03-25 | 2025-03-10 | 2025-03-15 | 2025-03-31 | 1 | NaOH | S11 | P1.0 | Underground | VA1-666-L-0001 | 666-0001-RMA-50-H1A-10 | RMA | SS 316 | H1A | 1 of 1 | 1 | FW | BW | J.01 | Spool 1 | 50 |  |  |  | Initial | T-Equal - Pipe | T-Equal SS 50 50 10S 316 2.77 | T-Equal | SS | 316 | 10S | 50 | 50 | 2.77 | T-Equal Stainless Steel 316 10S 50x50 | 1 | Ea | Sliding Support 370 50 011 | Sliding Support | 370 | 11 |  | 50 |  |  | Sliding Support 011 DN50 | 1 | Ea | [12 empty] | SR 0001 | 2025-04-01 | Hawking | 5 |  |  | 1 | [20 empty] | 2025-04-09 | Alex |  |  | 2025-04-15 | William | TSE-001 | 2025-04-11 | 1000 | ACC | 2025-04-18 | 2001 | ACC | [9 empty] | NaOH666-0001-RMA-50-H1A-10 SS 316 J.01
2025-03-01 | 2025-03-07 | 2025-03-25 | 2025-03-10 | 2025-03-15 | 2025-03-31 | 1 | NaOH | S11 | P1.0 | Underground | VA1-666-L-0001 | 666-0001-RMA-50-H1A-10 | RMA | SS 316 | H1A | 1 of 1 | 1 | FW | BW | J.02 | Spool 1 | 50 |  |  |  | Initial | Pipe - T-Piece | Pipe SS 50 10S 316 2.77 | Pipe | SS | 316 | 10S | 50 |  | 2.77 | Pipe Stainless Steel 316 10S DN50 2.77 | 0.5 | M | [23 empty] | SR 0001 | 2025-04-01 | Hawking | 60 |  |  | 1 | [20 empty] | 2025-04-09 | Alex |  |  | 2025-04-15 | William | TSE-002 | 2025-04-11 | 1001 | ACC | 2025-04-18 | 2001 | ACC | [9 empty] | NaOH666-0001-RMA-50-H1A-10 SS 316 J.02
2025-03-01 | 2025-03-07 | 2025-03-25 | 2025-03-10 | 2025-03-15 | 2025-03-31 | 1 | NaOH | S11 | P1.0 | Underground | VA1-666-L-0001 | 666-0001-RMA-50-H1A-10 | RMA | SS 316 | H1A | 1 of 1 | 1 | FW | BW | J.03 | Spool 1 | 50 |  |  |  | Initial | T-Piece - Pipe | T-Reducer SS 50 25 10S 316 2.77 | T-Reducer | SS | 316 | 10S | 50 | 25 | 2.77 | T-Reducer Stainless Steel 316 10S 50x25 | 1 | Ea | [23 empty] | SR 0001 | 2025-04-01 | Hawking | 4 |  |  | 1 | [20 empty] | 2025-04-09 | Alex |  |  | 2025-04-15 | William | TSE-003 | 2025-04-11 | 1002 | ACC | 2025-04-18 | 2001 | ACC | [9 empty] | NaOH666-0001-RMA-50-H1A-10 SS 316 J.03
2025-03-01 | 2025-03-07 | 2025-03-25 | 2025-03-10 | 2025-03-15 | 2025-03-31 | 1 | NaOH | S11 | P1.0 | Underground | VA1-666-L-0001 | 666-0001-RMA-50-H1A-10 | RMA | SS 316 | H1A | 1 of 1 | 1 | FW | BW | J.04 | Spool 1 | 50 |  |  |  | Initial | Pipe - T-Equal | Pipe SS 50 10S 316 2.77 | Pipe | SS | 316 | 10S | 50 |  | 2.77 | Pipe Stainless Steel 316 10S DN50 2.77 | 3.9 | M | T-Equal SS 50 50 10S 316 2.77 | T-Equal | SS | 316 | 10S | 50 | 50 | 2.77 | T-Equal Stainless Steel 316 10S 50x50 | 1 | Ea | [12 empty] | SR 0001 | 2025-04-01 | Hawking | 60 |  |  | 5 |  | SR 0001 | 2025-04-01 | Hawking | 5 |  |  | 1 | [12 empty] | 2025-04-09 | Alex |  |  | 2025-04-15 | William | TSE-004 | 2025-04-11 | 1003 | ACC | 2025-04-18 | 2001 | ACC | [9 empty] | NaOH666-0001-RMA-50-H1A-10 SS 316 J.04

## Updates from Engineer
PK | ADDED LINE NO | ADDED JOINT NO | DELETED LINE NO | DELETED JOINT NO | STATUS | DATE
NaOH666-0001-RMA-50-H1A-10 SS 316 J.01A | 666-0001-RMA-50-H1A-10 | J.01A |  |  | Added | 2025/03/05
NaOH666-0001-RMA-50-H1A-10 SS 316 J.01A | 666-0001-RMA-50-H1A-10 | J.01A |  |  | Added | 2025/03/05
NaOH666-0001-RMA-50-H1A-10 SS 316 J.02CRWA | 666-0001-RMA-50-H1A-10 | J.02CRWA |  |  | Added | 2025/03/05
NaOH666-0001-RMA-50-H1A-10 SS 316 J.01A |  |  | 666-0001-RMA-50-H1A-10 | J.01A | Deleted | 2025/03/05
NaOH666-0001-RMA-50-H1A-10 SS 316 J.02CRWA |  |  | 666-0001-RMA-50-H1A-10 | J.02CRWA | Deleted | 2025/03/05