## Monitoring Piping
LOI Date | KOM Date | Schedule | Welding Map Date | Receive Dwg | Start Fabric | LINE / DRAWING INFO | [11 empty] | DIA-INCH PLAN | [6 empty] | TOTAL | Comment | FIT-UP RECORD |  |  |  | WELDING RECORD
[6 empty] | NS | AREA | SYSTEM | PRIORITY | SUB AREA | DRAWING NO | LINE NO | LINE CODE | MAT'L LINE | MAT'L CODE | PAGE | DWG REV | FW / SW | BW / F / RING | JOINT NO | PIPE SPOOL | PIPE SIZE | DIA INCH |  |  |  | DIA INCH |  | DATE | SPV | DIA INCH |  | DATE | SPV | WELDER STAMP
[23 empty] | SW | FW |  |  | SW | FW |  |  | SW | FW
LOI Date | KOM Date | Schedule | Welding Map Date | Receive Dwg | Start Fabric | NS | AREA | System | Priority | Sub Area | Drawing No. | LINE NO | LINE CODE | MAT'L LINE | MAT'L CODE | PAGE | REV | FW / SW | JOINT TYPE | JOINT NO | PIPE SPOOL | DN | DIA-INCH PLAN SW | DIA-INCH PLAN FW | TOTAL | Comment | FIT-UP RECORD SW | FIT-UP RECORD FW | FIT-UP RECORD DATE | FU SPV | WELDING RECORD SW | WELDING RECORD FW | WELDING RECORD DATE | W SPV | W STAMP
2025-03-01 | 2025-03-07 | 2025-03-25 | 2025-03-10 | 2025-03-15 | 2025-03-31 | 1 | NaOH | S11 | P1.0 | Underground | VA1-666-L-0001 | 666-0001-RMA-50-H1A-10 | RMA | SS 316 | H1A | 1 of 1 | 1 | FW | BW | J.01 | Spool 1 | 50 |  |  |  | Initial |  |  | 2025-04-09 | Alex |  |  | 2025-04-05 | William | TSE-001
2025-03-01 | 2025-03-07 | 2025-03-25 | 2025-03-10 | 2025-03-15 | 2025-03-31 | 1 | NaOH | S11 | P1.0 | Underground | VA1-666-L-0001 | 666-0001-RMA-50-H1A-10 | RMA | SS 316 | H1A | 1 of 1 | 1 | FW | BW | J.02 | Spool 1 | 50 |  |  |  | Initial |  |  | 2025-04-09 | Alex |  |  | 2025-04-05 | William | TSE-002
2025-03-01 | 2025-03-07 | 2025-03-25 | 2025-03-10 | 2025-03-15 | 2025-03-31 | 1 | NaOH | S11 | P1.0 | Underground | VA1-666-L-0001 | 666-0001-RMA-50-H1A-10 | RMA | SS 316 | H1A | 1 of 1 | 1 | FW | BW | J.03 | Spool 1 | 50 |  |  |  | Initial |  |  | 2025-04-09 | Alex |  |  | 2025-04-05 | William | TSE-003
2025-03-01 | 2025-03-07 | 2025-03-25 | 2025-03-10 | 2025-03-15 | 2025-03-31 | 1 | NaOH | S11 | P1.0 | Underground | VA1-666-L-0001 | 666-0001-RMA-50-H1A-10 | RMA | SS 316 | H1A | 1 of 1 | 1 | FW | BW | J.04 | Spool 1 | 50 |  |  |  | Initial |  |  | 2025-04-09 | Alex |  |  | 2025-04-05 | William | TSE-004

## Conflict
LOI Date | KOM Date | Schedule | Welding Map Date | Receive Dwg | Start Fabric | LINE / DRAWING INFO | [11 empty] | DIA-INCH PLAN | [6 empty] | TOTAL | Comment | FIT-UP RECORD |  |  |  | WELDING RECORD
[6 empty] | NS | AREA | SYSTEM | PRIORITY | SUB AREA | DRAWING NO | LINE NO | LINE CODE | MAT'L LINE | MAT'L CODE | PAGE | DWG REV | FW / SW | BW / F / RING | JOINT NO | PIPE SPOOL | PIPE SIZE | DIA INCH |  |  |  | DIA INCH |  | DATE | SPV | DIA INCH |  | DATE | SPV | WELDER STAMP
[23 empty] | SW | FW |  |  | SW | FW |  |  | SW | FW
LOI Date | KOM Date | Schedule | Welding Map Date | Receive Dwg | Start Fabric | NS | AREA | System | Priority | Sub Area | Drawing No. | LINE NO | LINE CODE | MAT'L LINE | MAT'L CODE | PAGE | REV | FW / SW | JOINT TYPE | JOINT NO | PIPE SPOOL | DN | DIA-INCH PLAN SW | DIA-INCH PLAN FW | TOTAL | Comment | FIT-UP RECORD SW | FIT-UP RECORD FW | FIT-UP RECORD DATE | FU SPV | WELDING RECORD SW | WELDING RECORD FW | WELDING RECORD DATE | W SPV | W STAMP
2025-03-01 | 2025-03-07 | 2025-03-25 | 2025-03-10 | 2025-03-15 | 2025-03-31 | 1 | NaOH | S11 | P1.0 | Underground | VA1-666-L-0001 | 666-0001-RMA-50-H1A-10 | RMA | SS 316 | H1A | 1 of 1 | 1 | FW | BW | J.01A | Spool 1 | 50 | 0 | 2 | 2 | Client Req
2025-03-01 | 2025-03-07 | 2025-03-25 | 2025-03-10 | 2025-03-15 | 2025-03-31 | 1 | NaOH | S11 | P1.0 | Underground | VA1-666-L-0001 | 666-0001-RMA-50-H1A-10 | RMA | SS 316 | H1A | 1 of 1 | 1 | FW | BW | J.02CRWA | Spool 1 | 50 | 0 | 2 | 2 | Initial