## Monitoring Piping
LOI Date | KOM Date | Schedule | Welding Map Date | Receive Dwg | Start Fabric | LINE / DRAWING INFO | [11 empty] | DIA-INCH PLAN | [6 empty] | TOTAL | Comment | FIT-UP RECORD |  |  |  | WELDING RECORD |  |  |  |  | QA/QC REPORT
[6 empty] | NS | AREA | SYSTEM | PRIORITY | SUB AREA | DRAWING NO | LINE NO | LINE CODE | MAT'L LINE | MAT'L CODE | PAGE | DWG REV | FW / SW | BW / F / RING | JOINT NO | PIPE SPOOL | PIPE SIZE | DIA INCH |  |  |  | DIA INCH |  | DATE | SPV | DIA INCH |  | DATE | SPV | WELDER STAMP | AFI FIT UP |  |  | VISUAL
[23 empty] | SW | FW |  |  | SW | FW |  |  | SW | FW |  |  |  | F/U DATE | AFI NO | RES F/U | VIS DATE | AFI NO | RES VIS
LOI Date | KOM Date | Schedule | Welding Map Date | Receive Dwg | Start Fabric | NS | AREA | System | Priority | Sub Area | Drawing No. | LINE NO | LINE CODE | MAT'L LINE | MAT'L CODE | PAGE | REV | FW / SW | JOINT TYPE | JOINT NO | PIPE SPOOL | DN | DIA-INCH PLAN SW | DIA-INCH PLAN FW | TOTAL | Comment | FIT-UP RECORD SW | FIT-UP RECORD FW | FIT-UP RECORD DATE | FU SPV | WELDING RECORD SW | WELDING RECORD FW | WELDING RECORD DATE | W SPV | W STAMP | QAQC AFI F/U DATE | QAQC AFI F/U NO | QAQC AFI F/U RES | QAQC VISUAL DATE | QAQC VISUAL NO | QAQC VISUAL RES
2025-03-01 | 2025-03-07 | 2025-03-25 | 2025-03-10 | 2025-03-15 | 2025-03-31 | 1 | NaOH | S11 | P1.0 | Underground | VA1-666-L-0001 | 666-0001-RMA-50-H1A-10 | RMA | SS 316 | H1A | 1 of 1 | 1 | FW | BW | J.01 | Spool 1 | 50 |  |  |  | Initial |  |  | 2025-04-09 | Alex |  |  | 2025-04-15 | William | TSE-001 | 2025-04-11 | 1000 | ACC | 2025-04-18 | 2001 | ACC
2025-03-01 | 2025-03-07 | 2025-03-25 | 2025-03-10 | 2025-03-15 | 2025-03-31 | 1 | NaOH | S11 | P1.0 | Underground | VA1-666-L-0001 | 666-0001-RMA-50-H1A-10 | RMA | SS 316 | H1A | 1 of 1 | 1 | FW | BW | J.02 | Spool 1 | 50 |  |  |  | Initial |  |  | 2025-04-09 | Alex |  |  | 2025-04-15 | William | TSE-002 | 2025-04-11 | 1001 | ACC | 2025-04-18 | 2001 | ACC
2025-03-01 | 2025-03-07 | 2025-03-25 | 2025-03-10 | 2025-03-15 | 2025-03-31 | 1 | NaOH | S11 | P1.0 | Underground | VA1-666-L-0001 | 666-0001-RMA-50-H1A-10 | RMA | SS 316 | H1A | 1 of 1 | 1 | FW | BW | J.03 | Spool 1 | 50 |  |  |  | Initial |  |  | 2025-04-09 | Alex |  |  | 2025-04-15 | William | TSE-003 | 2025-04-11 | 1002 | ACC | 2025-04-18 | 2001 | ACC
2025-03-01 | 2025-03-07 | 2025-03-25 | 2025-03-10 | 2025-03-15 | 2025-03-31 | 1 | NaOH | S11 | P1.0 | Underground | VA1-666-L-0001 | 666-0001-RMA-50-H1A-10 | RMA | SS 316 | H1A | 1 of 1 | 1 | FW | BW | J.04 | Spool 1 | 50 |  |  |  | Initial |  |  | 2025-04-09 | Alex |  |  | 2025-04-15 | William | TSE-004 | 2025-04-11 | 1003 | ACC | 2025-04-18 | 2001 | ACC

## Updates from Engineer
PK | ADDED LINE NO | ADDED JOINT NO | DELETED LINE NO | DELETED JOINT NO | STATUS | DATE
NaOH666-0001-RMA-50-H1A-10 SS 316 J.01A | 666-0001-RMA-50-H1A-10 | J.01A |  |  | Added | 2025/03/05
NaOH666-0001-RMA-50-H1A-10 SS 316 J.01A | 666-0001-RMA-50-H1A-10 | J.01A |  |  | Added | 2025/03/05
NaOH666-0001-RMA-50-H1A-10 SS 316 J.02CRWA | 666-0001-RMA-50-H1A-10 | J.02CRWA |  |  | Added | 2025/03/05
NaOH666-0001-RMA-50-H1A-10 SS 316 J.01A |  |  | 666-0001-RMA-50-H1A-10 | J.01A | Deleted | 2025/03/05
NaOH666-0001-RMA-50-H1A-10 SS 316 J.02CRWA |  |  | 666-0001-RMA-50-H1A-10 | J.02CRWA | Deleted | 2025/03/05